## Pilot Overview
Pilot 2 | SIP creation and ingest of records
Task leader | National Archives of Norway
Supported by
Scope | Not less than 2 transfers of unstructured records with mixed restricted and unrestricted material, and not less than 1 transfer of structured records.
Object | Extract data from EDRMS and databases, create SIPs for structured and unstructured records using ESSArch Tools, ingest the SIPs to the repository using ESSArch Preservation Platform, for further evaluation
Short description | The main part of the pilot includes the export of electronic records and their metadata from EDRM systems and databases of Norwegian public sector institutions, transfer and ingest them to the NAN digital repository.
Timeframe | M28-M33
Preconditions | M03.3, M03.4 (DoW)
Contacts | Name (Title) | [9 empty] | E-mail | [9 empty] | Skype
Contact Person | Arne-Kristian Groven | [9 empty] | arngro@arkivverket.no
Pilot staff member | Terje Pettersen-Dahl | [9 empty] | geihau@arkivverket.no
Pilot staff member | Geir Haug | [9 empty] | tepe@arkivverket.no
Pilot staff member | Jørgen Ø. Vik-Strandli | [9 empty] | jorvik@arkivverket.no
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | X | E-ARK AIP |  |  | X | E-ARK DIP
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
|  |  |  | X | X |  |  |  |  | X
Pilot Scenarios
Scenario 1 | SIP Creation and Ingest of unstructured records (Data Set 1)
Scenario 2 | SIP Creation and Ingest of unstructured records (Data Set 2)
Scenario 3 | SIP Creation and Ingest of structured records (Data Set 3)
Success Criteria
General | The following E-ARK tools will be tested in a pilot environment: ESSArch Tools Producer (ETP), ESSArch Tools Archive (ETA), ESSArch Preservation Platform (EPP). This pilot will be considered a success if we are able to use and evaluate these tools in all three scenarios, producing an output that can be stored in depot. The National Archives of Norway have been using an earlier version of EPP in production for a couple of years, the ETP and ETA are newly developed software from which user experience will be gathered and dissminated during piloting.
Scenario 1 | SIP Creation and Ingest of unstructured records.
Scenario 2 | SIP Creation and Ingest of unstructured records.
Scenario 3 | SIP Creation and Ingest of structured records.

## Pilot Scenarios
Pilot 2 | Scenarios
Scenario 1 | SIP Creation and Ingest of unstructured records (Data Set 1)
Description | Extract unstructured records from EDRMS based on the Norwegian NOARK 4 standard. Create SIP using ESSArch Tools. Ingest the SIP to the repository using ESSArch Preservation Platform, for further evaluation.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | (X) | E-ARK AIP |  |  | (X) | E-ARK DIP
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
|  |  |  | X | X |  |  |  |  | X
Use-case | Extract and Ingest ERMS records (similar to MoReq2010)
Note
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]
Scenario 2 | SIP Creation and Ingest of unstructured records (Data Set 2)
Description | Extract unstructured records from EDRMS based on the Norwegian NOARK 5 standard. Create SIP using ESSArch Tools. Ingest the SIP to the repository using ESSArch Preservation Platform, for further evaluation
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | (X) | E-ARK AIP |  |  | (X) | E-ARK DIP
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
|  |  |  | X | X |  |  |  |  | X
Use-case | Extract and Ingest ERMS records (similar to MoReq2010)
Note
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]
Scenario 3 | SIP Creation and Ingest of structured records (Data Set 3)
Description | Extract data from old database output, create SIPs for structured records using ESSArch Tools, ingest the SIPs to the repository using ESSArch Preservation Platform, for further evaluation.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | (x) | E-ARK AIP |  |  | (X) | E-ARK DIP
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
|  |  |  | X | X |  |  |  |  | X
Use-case | Old database (CSV representation)
Note | Extract rows and tables from DB and create SIP.
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]

## Pilot Data
Pilot 2 | Pilot Data
Information Packages (IP) | IP |  | Note
| E-ARK SIP | (x) | In additional scenario
| non E-ARK SIP | x | Due to production requirements
| E-ARK AIP | (x) | In additional scenario
| non E-ARK AIP | x | Due to production requirements
E-ARK DIP
non E-ARK DIP
Pilot data description
Data Set 1 | Noark 4 output from EDRMS
Description | EDRMS data from public producer converted into Noark 4 output (real production data)
Data type | Noark 5 XML file, documents in PDF/A (or a few other specified formats), in TAR file
Metadata format | XML: METS, PREMIS, ADDML (local)
Quantity | 20GB
Data Set 2 | Noark 5 output from EDRMS
Description | EDRMS data public producer converted into Noark 5 output (real production data)
Data type | Noark 5 XML file, documents in PDF/A (or a few other specified formats), in TAR file
Metadata format | XML: METS, PREMIS, ADDML (local)
Quantity | 5 GB
Data Set 3 | Old database (CSV)
Description | The data set here is the national registry of licenced hunters containing data from the period 1985-1999.
Data type | CSV format (input), tar file
Metadata format | XML: METS, PREMIS, ADDML (local)
Quantity | Containing 338.500 registred persons. 105 MB

## Pilot preparation
Pilot 2 | Pilot Preparation
Preparation status
Software component | Tool / Version number | Scenario | Process | Tool selected | Tool available for Pilot | Tool/Version installation | Tool configuration | Knowledge overtaken | Tool ready for Pilot
Preparation tasks related to the software components | from Software Component Matrix (for E-.ARK tools) | from Scenarios sheet | from Processes sheets | Yes /No / (issue) | Yes / (planned date of availability) | Installed / (issues) | No needed / Configured / (issues) | Yes / (issues) | Ready / (issues)
ESSArch Tools Producer (ETP) |  | 1,2,3 | pre-ingest |  |  | We will need to install it | We will need to configure |  | No, some issues left
ESSArch Tools Archive (ETA) |  | 1,2,3 | pre-ingest |  |  | We will need to install it | We will need to configure |  | No, some issues left
ESSArch Preservation Platform (EPP) |  | 1,2,3 | ingest |  |  | We will need to install it | We will need to configure |  | No, some issues left
Prepration status
Pilot dataset | Dataset # | Scenario | Data selected | Legal issues | Data available | Dataset ready for Pilot
Preparation tasks related to pilot data | from Pilot Data sheet | from Scenarios sheet | Yes / (issues) | None / (issue) | Yes / (planned date) / (issue) | Ready / (issue)
Noark 4 EDRMS output | Data set 1 | 1 | Yes | None | May | August
Noark 5 EDRMS output | Data set 2 | 2 | Yes | None | May | August
Registry of licenced hunters | Data set 3 | 3 | Yes | None | May | August
Prepration status
Infrastructure | Scenario | Process | Element selected | Issues | Element ready for Pilot
Preparation tasks related to pilot infrastructure | from Scenarios sheet | from Processes sheets | Yes / (issues) | None / (issue) | Ready / (issue)
Server installation/config | 1,2,3 | Pre-ingest, Ingest |  |  | Yes/May
Tool installation/config | 1,2,3 | Pre-ingest, Ingest |  |  | Yes/August
Note on A4: Please, list all relevant E-ARK and local software components. Example: - Data Preservation Toolkit - XIP Creator (local)
Note on C4: Please, select the scenario from the Pilot Scenarios sheet in which the tool is used
Note on D4: Please, select the process from the processes sheets in which the tool is used. Example: - Pre-Ingest - Access
Note on E4: Please, indicate whether the tool has benn selected (yes) or not yet (no), and any issues related tool selection (like: "Testing tool candidates")
Note on F4: Examples: - Yes - 01/04/2016 - No date available
Note on G4: Examples: - Installed - Planned at 01/04/2016 - Installation issues - No instal kit available
Note on H4: Examples: - No configuration needed - Configured - Configuration issues
Note on I4: Examples: - Yes - Training required - Further knowledge transfer needed - User Manual not available
Note on A16: Please list every data set from the Pilot Data sheet
Note on C16: Please, select the scenario from the Pilot Scenarios sheet in which the dataset is used
Note on D16: Please indicate wheather the data set has been selected yet
Note on E16: Example: - None - Under contracting with provider - Under negotiaitions with provider
Note on F16: Example: - Yes - 01/04/2016 - dataset not available by provider - access issues
Note on A23: Please list all infrastructure components that are relevant (and not obvious) for the pilot Like - special hardware elements - special database elements - special data viewers (not provided by E-ARK)
Note on B23: Please, select the scenario from the Pilot Scenarios sheet in which this infrastructure component is used
Note on C23: Please, select the process from the processes sheets in which this infrastructure component is used. Example: - Pre-Ingest - Access
Note on D23: Please indicate wheather the element has been selected yet

## Pre-Ingest
OAIS Process | Pre-Ingest
Main Process Stepps | Content definition Technical feasibility Legal issues etc. | Create/Review transfer agreement | Select data | Data Extraction | Manual compilation of non ERMS content | Metadata mapping | Create SIP | Post-packaging quality control | Submit SIP
Scenario 3 | Structured data, not ERMS
Used E-ARK tool | [5 empty] | ETP | ETP | ETP | ETP
Used local tools
Perfomer (actor) | [5 empty] | Producer, Archivist | Producer, Archivist | Producer, Archivist | Producer, Archivist
Prelemineries and Start condition
Input | [6 empty] | Metadata | E-ARK SIP | E-ARK SIP
Output | [5 empty] | Metadata | E-ARK SIP | Quality report
Scenario 1,2 | SIP Creation and Ingest of ERMS files
Used E-ARK tool | [5 empty] | ETP | ETP | ETP | ETP
Used local tools |  |  | NOARK 5 extraction tool | NOARK 5 extraction tool
Perfomer (actor) |  |  | Producer | Producer |  | Producer, Archivist | Producer, Archivist | Producer, Archivist | Producer, Archivist
Prelemineries and Start condition
Input |  |  |  | Selected data |  | Extracted data | Metadata | E-ARK SIP | E-ARK SIP
Output |  |  | Selected data | Extracted data |  | Metadata | E-ARK SIP | Quality report

## Ingest
OAIS Process | Ingest
Main Process Stepps | Receive SIP | Security check | Integrity check | Sintax check | Format check | Review and Approve SIP | Modify SIP | Generate and Store AIP
Scenario 3 | Structured data, not ERMS
Used E-ARK tool | ETA |  | ETA, EPP |  |  | EPP |  | EPP
Used local tools |  | Local tools |  | Arkade 4 | Arkade 4
Perfomer (actor) | Archive | Archive | Archive | Archive | Archive | Archive |  | Archive
Prelemineries and Start condition
Input | E-ARK SIP | E-ARK SIP | E-ARK SIP | E-ARK SIP | E-ARK SIP | E-ARK SIP |  | E-ARK SIP
Output |  | check report | check report | check report | check report | Approved SIP |  | E-ARK AIP
Scenario 1,2 | SIP Creation and Ingest of ERMS files
Used E-ARK tool | ETA |  | ETA, EPP |  |  | EPP |  | EPP
Used local tools |  | (yes) |  | Arkade 4, ArkN4 | Arkade 4
Perfomer (actor) | Archive | Archive | Archive | Archive | Archive | Archive |  | Archive
Prelemineries and Start condition
Input | E-ARK SIP | E-ARK SIP | E-ARK SIP | E-ARK SIP | E-ARK SIP | E-ARK SIP |  | E-ARK SIP
Output |  | check report | check report | check report | check report | Approved SIP |  | E-ARK AIP

## Backup Lists
OAIS Processes
Pre-Ingest
Ingest
Preservation
Data Management
Access
IP Formats
E-ARK SIP format
non-E-ARK SIP format
E-ARK AIP format
non-E-ARK AIP format
E-ARK DIP format
non-E-ARK DIP format
Pre-Ingest Use-cases
Extract and Ingest relational database based on SIARD 2.0
Extract and Ingest ERMS records based on MoReq2010
Extract and Ingest computer files from simple file-system - GML
Extract and Ingest computer files from simple file-system - Other (please specify)
Other (please specify in the Note field)
Native metadata format of producer system
MoReq 2
MoReq 2010
ApeEAD
EAD 1
EAD 2
EAD 3
Other (Please specify in the Note field)
Pre-Ingest Process Steps
Content definition, technical feasibility, legal issues, etc.
Create/review transfer agreement
Select data
Manual compilation of non ERMS content
Data extraction
Metadata mapping
Create SIP
Post-packaging control
Submit SIP
Receive SIP
Security check
Formal validation
Content review and approval
Modify SIP
Generate and store AIP
Search & Order Management
DIP Preparation
DIP Delivery
DIP Management
Other (please specifiy)
Pre-Ingest / Ingest Tools
Alfresco Export Module for MoReq2010-based extraction
ESSArch Tools for SIP preparation and creation
Database Preservation Toolkit for creating SIARD2.0 from relational
SIP-AIP Module
Other non-E-ARK tool (please specify)
Access Tools
Search Module
Order Module
DIP Management Module
AIP-DIP Module
Presentation Module
Other non-E-ARK tool (please specify)
Access Use-cases
Access databases via Sofia (sql)
Access databases via SOLR (no-sql)
Access single ERMS records via alfresco cms
Access geodata via qgis
Access data with OLAP via oracle
Other (please specify content type and presentation tool)