## Pilot Overview
Pilot 5 | Preservation and access to records with geodata
Task leader | National Archives of Slovenia
Supported by | Danish National Archives
Scope | Pilot will prove that the SIP and DIP implementations fulfill specific requirements for the records containing GIS data, test the instructions (for the producer and for the archive) regarding all phases of ingest, to prove that the archival use of GIS data is possible (via open data method, direct access in the archives and use GIS data as search criteria in the DIP contents).
Object | Pilot report with recommendations about urgent improvements and possible future improvements support for WP6 & WP7 setting up the work environment of selected E-ARK archival tools provide real life examples how the project deliverables can be used
Short description | During the e-ARK project the standardized method for ingesting geo data will be developed. This will allow the archives to offer geodata as a selection and display criteria of records by means of integration of current state of the art tools.
Timeframe | M25-M27: setting up the pilot sites; M28-M31: running the pilots; M32-M33: testing and reporting
Preconditions | M03.3, M03.4, M04.2, M05.4, M05.6 (DoW)
Contacts | Name (Title) | [9 empty] | E-mail | [9 empty] | Skype
Contact Person | Gregor Završnik () | [9 empty] | gregor.zavrsnik@gov.si | [9 empty] | gregor.zavrsnik
Pilot staff member | Alenka Starman () | [9 empty] | alenka.starman@gov.si
Pilot staff member | Joze Skofljanec () | [9 empty] | joze.skofljanec@gov.si
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | X | E-ARK AIP |  |  | X | E-ARK DIP | [15 empty] | X
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | Catalogue (E-ARK Web) | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
|  |  |  | X | X |  |  |  |  | X |  | X | X | X | X | X | X | X |  |  | X |  |  |  | X | X | X
Pilot Scenarios
Scenario 1 | SIP Creation and Ingest of records with geodata (2 representations)
Scenario 2 | Search and Access information using Geodata (2 representations)
Scenario 3 | SIP Creation and Ingest of records with Geodata (1 representation)
Scenario 4 | Search and Access information using Geodata (1 representation)
Success Criteria
General | The following E-ARK tools will be tested in a pilot environment: ESSArch Tools Producer (ETP), ESSArch Tools Archive (ETA), ESSArch Preservation Platform (EPP), OMT - Search and Dsiplay GUI, OMT - Order Management Tool , IP Viewer, along with components of the Integrated Protoype (E-ARK Web): Order Submission Service, Lily-Ingest, Geoserver, Peripleo, with the integration of an Archival EAD based Catalogue and QGIS (Yes/No)
Scenario 1 | SIP creation, verification and ingest of more then 1000 records with a vector geodata layer. (90% success rate)
Scenario 2 | Finding , accessing, modifying and exporting a DIP containing a vector geodata layer of more then 1000 records. (90% success rate)

## Pilot Scenarios
Pilot 5 | Scenarios
Scenario 1 | SIP Creation and Ingest of records with Geodata
Description | Create SIP from records and metadata exported from GURS (The Surveying and Mapping Authority of the Republic of Slovenia). SIP creation and ingest of at least one vector geodata with at least 1000 records Archivist creates a Submission agreement for SIP creation, according to E-ARK guidelines for geodata SIP creation. Producer creates a SIP containing geodata, acording to Submission agreement, based on EARK SIP specifications for geodata. Archivist technicaly validates the submited SIP package, according to E-ARK guidelines for geodata SIP creation. Archivist confirms, that content validation of the submited SIP package was performed. An AIP is generated from the SIP and gets ingested into the archival repository.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | X | E-ARK AIP |  |  | X | E-ARK DIP
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | Catalogue (E-ARK Web) | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
|  |  | X |  | X |  |  |  |  | X
Use-case | Extract and Ingest computer files from simple file-system - GML
Note | SIP Creation and Ingest of records with Geodata
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]
Scenario 2 | Search and Access information using Geadota
Description | Create DIP from AIP containing record with Geodata. Present Geodata information with QGIS along with content and metadata from DIP. A data object containing geodata can be identified by using search criteria as specified by E-ARK Tool requirement specification. Selected data objects are selected and order is issued. DIP is prepared according to order specification and end user credentials. DIP file structure with file descriptions (mime type, short description) is presented to the enduser. Geodata from the order can be accessed in the designated viewer (QGIS). The user checks authenticity of the DIP by accessing PREMIS documentation. Access to DIP is documented and captured metadata can be exported.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [6 empty] | E-ARK AIP |  |  | X | E-ARK DIP | [15 empty] | X
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | Catalogue (E-ARK Web) | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
[12 empty] | X | X | X | X | X | X | X |  |  | X |  |  |  | X | X | X
Use-case | Access geodata via QGIS
Note | Access records with Geodata and present geodata with QGIS
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]
Scenario 3 | SIP Creation and Ingest of records with Geodata
Description | Create SIP from records and metadata exported from ARSO (Environmental Agency of Republic of Slovenia). SIP creation and ingest of at least one vector geodata with at least 1000 records. Data iz exported directly from their own system into GML format. And their sistem also exports INSPIRE metadata. Archivist creates a Submission agreement for SIP creation, according to E-ARK guidelines for geodata SIP creation. Producer creates a SIP containing geodata, acording to Submission agreement, based on EARK SIP specifications for geodata. Archivist technicaly validates the submited SIP package, according to E-ARK guidelines for geodata SIP creation. Archivist confirms, that content validation of the submited SIP package was performed. An AIP is generated from the SIP and gets ingested into the archival repository.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | X | E-ARK AIP |  |  | X | E-ARK DIP
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | Catalogue (E-ARK Web) | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
|  |  |  | X | X |  |  |  |  | X
Use-case | Extract and Ingest computer files from simple file-system - GML
Note | SIP Creation and Ingest of records with Geodata
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]
Scenario 4 | Search and Access information using Geadota
Description | Create DIP from AIP containing record with Geodata. Present Geodata information with QGIS along with content and metadata from DIP. A data object containing geodata can be identified by using search criteria as specified by E-ARK Tool requirement specification. Selected data objects are selected and order is issued. DIP is prepared according to order specification and end user credentials. DIP file structure with file descriptions (mime type, short description) is presented to the enduser. Geodata from the order can be accessed in the designated viewer (QGIS). The user checks authenticity of the DIP by accessing PREMIS documentation. Access to DIP is documented and captured metadata can be exported.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [6 empty] | E-ARK AIP |  |  | X | E-ARK DIP | [15 empty] | X
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | Catalogue (E-ARK Web) | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
[12 empty] | X | X | X | X | X | X | X |  |  | X |  |  |  | X | X | X
Use-case | Access geodata via QGIS
Note | Access records with Geodata and present geodata with QGIS
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]

## Pilot Data
Pilot 5 | Pilot Data
Information Packages (IP) | IP |  | Note
| E-ARK SIP | x | Focusing on Geodata preservation
non E-ARK SIP
| E-ARK AIP | x | Focusing on Geodata preservation
non E-ARK AIP
| E-ARK DIP | x | Focusing on Geodata access
non E-ARK DIP
Pilot data description
Data Set 1 | Records and metadata of administrative units until 1994 exported from GURS (The Surveying and Mapping Authority of the Republic of Slovenia)
Description | Records and metadata of maps with Geodata
Data type | GML document with metadata in XML format, ESRI Shapefile, csv
Metadata format | ISO 19115 (INSPIRE)
less | 62 records (cca. 3MB)
Data Set 2 | Records and metadata of Natura 2000 areas, exported from ARSO
Description | Records and metadata of maps with Geodata
Data type | GML document with metadata in XML format
Metadata format | ISO 19115 (or INSPIRE)
less | 1209 records (cca. 10 MB)

## Pilot preparation
Pilot 5 | Pilot Preparation
Preparation status
Software component | Tool / Version number | Scenario | Process | Tool selected | Tool available for Pilot | Tool/Version installation | Tool configuration | Knowledge overtaken | Tool ready for Pilot
Preparation tasks related to the software components | from Software Component Matrix (for E-.ARK tools) | from Scenarios sheet | from Processes sheets | Yes /No / (issue) | Yes / (planned date of availability) | Installed / (issues) | No needed / Configured / (issues) | Yes / (issues) | Ready / (issues)
Component 1. | ESSArchive ETP | Scenario 1, 3 | Pre-ingest | Yes | Yes | Not installed | Need support form ESS | Basic training completed | No, local installation needed
Component 2. | ESSArchive ETA | Scenario 1, 3 | Ingest | Yes | Yes | Not installed | Need support form ESS | Basic training completed | No, local installation needed
Component 3. | ESSArchive EPP | Scenario 1, 3 | Ingest (Access?) | Yes | Yes | Not installed | Need support form ESS | Training in progres | EAD Support, Some validation features
Component 4. | Integrated Platform (EARK WEB) | Scenario 1, 2, 3, 4 | Ingest, Access | Yes | No | Not installed | Need support form AIT | Training required | ???
Component 5. | QGIS | Scenario 1, 2, 3, 4 | Pre-Ingest, Ingest, Access | Yes | Yes | Installed | None needed | Yes | Yes
Component 6. | Inspire metadata editor | Scenario 1 | Pre-ingest | Yes | Yes | Online | None needed | Yes | Yes
Component 7. | EAD metadata editor | Scenario 1, 3 | Ingest | No | No | Not installed | Need support form ESS | Further knowladge transfer required | ???
Component 8. | Search and display GUI | Scenario 2, 4 | Access | No | No | Not installed | Need support form AIT | Further knowladge transfer requires | NO
Component 9. | Peripleo | Scenario 1, 2, 3, 4 | Ingest, Access | Yes | Yes / in 2/2 April | Not installed | Need support from AIT | Further knowladge transfer requires | Yes
Component 10. | OMT | Scenario 2, 4 | Access | No | No | Not installed | Need support form Magenta | Further knowladge transfer requires | NO
Component 11. | Archival Catalogue (EAD based) | Scenario 1, 2, 3, 4 | Ingest, Access | No | No | Not installed | Need input | Further knowladge transfer requires | NO
Component 12. | Lilly | Scenario 1, 2, 3, 4 | Ingest, Access | Yes | Yes / in 2/2 April | Not installed | Need support from AIT | Further knowladge transfer requires | Yes
Component 13. | Geoserver | Scenario 2, 4 | Access | Yes | Yes | Installed | None needed | Yes | Yes
Prepration status
Pilot dataset | Dataset # | Scenario | Data selected | Legal issues | Data available | Dataset ready for Pilot
Preparation tasks related to pilot data | from Pilot Data sheet | from Scenarios sheet | Yes / (issues) | None / (issue) | Yes / (planned date) / (issue) | Ready / (issue)
Slovenian Register of spatial units selected dataset layers | Data set 1 | 1.2 | Yes | None | Yes | Yes
Natura 2000 dataset | Data set 2 | 3.4 | Yes | None | Yes | Yes
…
Prepration status
Infrastructure | Scenario | Process | Element selected | Issues | Element ready for Pilot
Preparation tasks related to pilot infrastructure | from Scenarios sheet | from Processes sheets | Yes / (issues) | None / (issue) | Ready / (issue)
Virtual server - Linux
…
Note on A4: Please, list all relevant E-ARK and local software components. Example: - Data Preservation Toolkit - XIP Creator (local)
Note on C4: Please, select the scenario from the Pilot Scenarios sheet in which the tool is used
Note on D4: Please, select the process from the processes sheets in which the tool is used. Example: - Pre-Ingest - Access
Note on E4: Please, indicate whether the tool has benn selected (yes) or not yet (no), and any issues related tool selection (like: "Testing tool candidates")
Note on F4: Examples: - Yes - 01/04/2016 - No date available
Note on G4: Examples: - Installed - Planned at 01/04/2016 - Installation issues - No instal kit available
Note on H4: Examples: - No configuration needed - Configured - Configuration issues
Note on I4: Examples: - Yes - Training required - Further knowledge transfer needed - User Manual not available
Note on B12: If E-ARK PRE-INGEST tools do not support EAD creation we need a special tool for that
Note on A21: Please list every data set from the Pilot Data sheet
Note on C21: Please, select the scenario from the Pilot Scenarios sheet in which the dataset is used
Note on D21: Please indicate wheather the data set has been selected yet
Note on E21: Example: - None - Under contracting with provider - Under negotiaitions with provider
Note on F21: Example: - Yes - 01/04/2016 - dataset not available by provider - access issues
Note on A28: Please list all infrastructure components that are relevant (and not obvious) for the pilot Like - special hardware elements - special database elements - special data viewers (not provided by E-ARK)
Note on B28: Please, select the scenario from the Pilot Scenarios sheet in which this infrastructure component is used
Note on C28: Please, select the process from the processes sheets in which this infrastructure component is used. Example: - Pre-Ingest - Access
Note on D28: Please indicate wheather the element has been selected yet

## Pre-Ingest
OAIS Process | Pre-Ingest
Main Process Stepps | Content definition Technical feasibility Legal issues etc. | Create/Review transfer agreement | Select data | Data Extraction | Manual compilation of non ERMS content | Metadata mapping | Create SIP | Post-packaging quality control | Submit SIP
Scenario 1 | SIP Creation and Ingest of geodata in GML format
Used E-ARK tool |  |  |  | QGIS |  |  | ESS Arch ETP |  | ESS Arch ETP
Used local tools |  |  | Existing archival system | Producers tools | Producer tools, open convesion tools | MS Excel, Inspire Metadata Creator
Perfomer (actor) |  | Producer + Archivist + Technical Specialist | Producer | Producer | Producer | Producer | Producer |  | Producer
Prelemineries and Start condition |  | Official archival records definition
Input |  | Official archival records definition and technical documentation | Submission Agreement | Submission Agreement | Subission Agreement | INSPIRE.xml, Submission Agreement, MS Excel template for EAD conversion | Extracted data Additional Data and documentation Inspire.xml, MS excel w. metadata |  | Subission Agreement, SIP
Output |  | Submission Agreement | Data selection list | Extracted data | Additional Data and documentation | Inspire.xml, MS excel w. metadata | E-ARK SIP |  | Submited SIP
Scenario 3 | SIP Creation and Ingest of geodata in GML format
Used E-ARK tool | [6 empty] | ESS Arch ETP |  | ESS Arch ETP
Used local tools |  |  | Existing system | Producers tools | Producer tools | Producer GIS system, MS Excel
Perfomer (actor) |  | Producer + Archivist + Technical Specialist | Producer | Producer | Producer | Producer | Producer |  | Producer
Prelemineries and Start condition |  | Official archival records definition
Input |  | Official archival records definition and technical documentation | Submission Agreement | Submission Agreement | Subission Agreement | INSPIRE.xml, Submission Agreement, MS Excel template for EAD conversion | Extracted data Additional Data and documentation Inspire.xml, MS excel w. metadata |  | Subission Agreement, SIP
Output |  | Submission Agreement | Data selection list | Extracted data | Additional Data and documentation | Inspire.xml, MS excel w. metadata | E-ARK SIP |  | Submited SIP

## Ingest
OAIS Process | Ingest
Main Process Stepps | Receive SIP | Security check | Integrity check | Sintax check | Format check | Review and Approve SIP | Modify SIP | Generate and Store AIP
Scenario 1 | SIP Creation and Ingest of old (not normalized) database in SIARD 2.0 format
Used E-ARK tool | ESS Arch ETA | ESS Arch EPP | ESS Arch EPP | ESS Arch EPP + GML schema validator | ESS Arch EPP | ESS Arch EPP and QGIS | EAD Editor, Archival Catalogue | ESSArc EPP + integrated platform + Peripleo + Lilly
Used local tools | [5 empty] | Local SFBS file viewers
Perfomer (actor) | Archivist | Archivist | Archivist | Archivist | Archivist | Archivist | Archivist | Archivist
Prelemineries and Start condition | [6 empty] | SIP is approved
Input | SIP from Producer | SIP from Producer | SIP from Producer | SIP from Producer | SIP from Producer | SIP from Producer | Aproved SIP | Aprooved SIP + Archival EAD
Output | Validated SIP + Report | Validated SIP + Report | Validated SIP + Report | Validated SIP + Report | Validated SIP + Report | Aproved SIP | SIP + Catalogue metadata | AIP + Search Indexes in Peripleo and Lilly
Scenario 3 | SIP Creation and Ingest of old (not normalized) database in SIARD 2.0 format
Used E-ARK tool | ESS Arch ETA | ESS Arch EPP | ESS Arch EPP | ESS Arch EPP + GML schema validator | ESS Arch EPP | ESS Arch EPP and QGIS | EAD Editor, Archival Catalogue | ESSArc EPP + integrated platform + Peripleo + Lilly
Used local tools | [5 empty] | Local SFBS file viewers
Perfomer (actor) | Archivist | Archivist | Archivist | Archivist | Archivist | Archivist | Archivist | Archivist
Prelemineries and Start condition | [6 empty] | SIP is approved
Input | SIP from Producer | SIP from Producer | SIP from Producer | SIP from Producer | SIP from Producer | SIP from Producer | Aproved SIP | Aprooved SIP + Archival EAD
Output | Validated SIP + Report | Validated SIP + Report | Validated SIP + Report | Validated SIP + Report | Validated SIP + Report | Aproved SIP | SIP + Catalogue metadata | AIP + Search Indexes in Peripleo and Lilly

## Access
OAIS Process | Access
Main Process Stepps | Search & Select Records | Manage Order | Prepare DIP | Prepare DIP delivery | Deliver DIP | Access DIP | DIP Management
Scenario 2 | Access Geodata from DIP0
Used E-ARK tool | Search and display GUI, Peripleo, LILY, Archival Catalogue | OMT | QGIS | QGIS + IP Viewer | OMT | QGIS + IP Viewer | OMT
Used local tools |  |  | Local SFBS file tools
Perfomer (actor) | User | Archivist | Archivist | Archivist |  | User | Archivist
Prelemineries and Start condition | User is verifyed and registred | User is allowed acces to requested records | User credentials
Input | EAD Catalog, search Index | Order.xml | Order.xml | DIP0 /DIPp, Order.xml | DIPu | DIPu | DIPu
Output | Order.xml | Order.xml approved | DIP0 /DIPp | DIPu | Use and access metadata | Use and access metadata | DIPp, deleted DIPu
Scenario 4 | Access Geodata from DIP0
Used E-ARK tool | Search and display GUI, Peripleo, LILY, Archival Catalogue | OMT | QGIS | QGIS + IP Viewer | OMT | QGIS + IP Viewer | OMT
Used local tools |  |  | Local SFBS file tools
Perfomer (actor) | User | Archivist | Archivist | Archivist |  | User | Archivist
Prelemineries and Start condition | User is verifyed and registred | User is allowed acces to requested records | User credentials
Input | EAD Catalog, search Index | Order.xml | Order.xml | DIP0 /DIPp, Order.xml | DIPu | DIPu | DIPu
Output | Order.xml | Order.xml approved | DIP0 /DIPp | DIPu | Use and access metadata | Use and access metadata | DIPp, deleted DIPu

## Backup Lists
OAIS Processes
Pre-Ingest
Ingest
Preservation
Data Management
Access
IP Formats
E-ARK SIP format
non-E-ARK SIP format
E-ARK AIP format
non-E-ARK AIP format
E-ARK DIP format
non-E-ARK DIP format
Pre-Ingest Use-cases
Extract and Ingest relational database based on SIARD 2.0
Extract and Ingest ERMS records based on MoReq2010
Extract and Ingest computer files from simple file-system - GML
Extract and Ingest computer files from simple file-system - Other (please specify)
Other (please specify in the Note field)
Native metadata format of producer system
MoReq 2
MoReq 2010
ApeEAD
EAD 1
EAD 2
EAD 3
Other (Please specify in the Note field)
Pre-Ingest Process Steps
Content definition, technical feasibility, legal issues, etc.
Create/review transfer agreement
Select data
Manual compilation of non ERMS content
Data extraction
Metadata mapping
Create SIP
Post-packaging control
Submit SIP
Receive SIP
Security check
Formal validation
Content review and approval
Modify SIP
Generate and store AIP
Search & Order Management
DIP Preparation
DIP Delivery
DIP Management
Other (please specifiy)
Pre-Ingest / Ingest Tools
Alfresco Export Module for MoReq2010-based extraction
ESSArch Tools for SIP preparation and creation
Database Preservation Toolkit for creating SIARD2.0 from relational
SIP-AIP Module
Other non-E-ARK tool (please specify)
Access Tools
Search Module
Order Module
DIP Management Module
AIP-DIP Module
Presentation Module
Other non-E-ARK tool (please specify)
Access Use-cases
Access databases via Sofia (sql)
Access databases via SOLR (no-sql)
Access single ERMS records via alfresco cms
Access geodata via qgis
Access data with OLAP via oracle
Other (please specify content type and presentation tool)