## Pilot Overview
Pilot 4 | Business Archives
Task leader | National Archives of Estonia
Supported by | Estonian Business Archives
Scope | Pre-ingest preparation and transfer of business records to a digital archive solution in a business archive
Object | bespoke business system that contains database records
Short description | Estonian Business Archives, Llc. is a privately owned archiving services provider. The main client base of the company is comprised of private businesses in Estonia for archiving and preservation of both paper and digital records. The business archives pilot in the E-ARK project will focus on transfer of database records from a private company to the digital archive solution of the Estonian Business Archives.
Timeframe | M25-M27: setting up the pilot sites; M28-M31: running the pilots; M32-M33: testing and reporting.
Preconditions | 03.3, M03.4, M04.2, M05.4, M05.6 (DoW)
Contacts | Name (Title) | [9 empty] | E-mail | [9 empty] | Skype
Contact Person | Raivo Ruusalepp | [9 empty] | raivo@eba.ee | [9 empty] | raivoruu
Pilot staff member | Ats Rand | [9 empty] | ats.rand@eba.ee | [9 empty] | atsrand
Pilot staff member
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | X | E-ARK AIP |  |  |  | E-ARK DIP
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer) | CMIS portal/viewer
X
Pilot Scenarios
Scenario 1 | Migration and Ingest of business data from bespoke business system
Success Criteria
General | The following E-ARK tools were tested in a pilot environment: Database Preservation Toolkit (Done) RODA-In (Not done due lack of interest and need)
Scenario 1 | Exporting records from database for more than 12 000 business records from bespoke business system
Scenario 2 | Importing records to database for more than 12 000 business records from bespoke business system
Scenario 3 | Exporting records from database with files for more than 200 000 business records from bespoke business system (success rate 85% due complicated database architecture)
Scenario 4 | Importing records to database with files for more than 200 000 business records from bespoke business system (success rate 85% due complicated database architecture)

## Pilot Scenarios
Pilot 4 | Scenarios
Scenario 1 | Migration and Ingest of business records from bespoke business system
Description | Export business records from bespoke business system. Ingest to local archival system of EBA.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | X | E-ARK AIP |  |  |  | E-ARK DIP
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer) | CMIS portal/viewer
X
Use-case | Extract and Ingest relational database based on SIARD 2.0
Note
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]
Scenario 2 | Import business records from SIARD 2.0
Description | Import business records from SIARD2.0 to bespoke business system.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | X | E-ARK AIP |  |  |  | E-ARK DIP
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer) | CMIS portal/viewer
X
Use-case | Access databases via DBVTK (SQL)
Note
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]
Scenario 3 | Migration and Ingest of business records from bespoke business system
Description | Export business records from bespoke business system. Ingest from external system.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | X | E-ARK AIP |  |  |  | E-ARK DIP
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer) | CMIS portal/viewer
X
Use-case | Extract and Ingest relational database based on SIARD 2.0
Note
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]
Scenario 4 | Import business records from SIARD 2.0
Description | Import business records from SIARD2.0 to bespoke business system.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | X | E-ARK AIP |  |  |  | E-ARK DIP
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer) | CMIS portal/viewer
X
Use-case | Access databases via DBVTK (SQL)
Note
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]

## Pilot Data
Pilot 4 | Pilot Data
Information Packages (IP) | IP |  | Note
| E-ARK SIP | x
| non E-ARK SIP | x | Format of local archival system of EBA
E-ARK AIP
| non E-ARK AIP | x | Format of local archival system of EBA
E-ARK DIP
non E-ARK DIP
Pilot data description
Data Set 1 | Records from bespoke business system
Description | Business system with 14 tables. The database contains approximately 12 000 records.
Data type | MS-SQL as mdf
Metadata format | none
Quantity | more than 12 000 rows
Data Set 2 | Records from bespoke business system
Description | Business system with 63 tables (+several history and support tables that are not needed for a complete structure of the working database). The database contains approximately 200 000 records.
Data type | MS-SQL as mdf
Metadata format | none
Quantity | more than 200 000 rows

## Pilot preparation
Pilot 4 | Pilot Preparation
Preparation status
Software component | Tool / Version number | Scenario | Process | Tool selected | Tool available for Pilot | Tool/Version installation | Tool configuration | Knowledge overtaken | Tool ready for Pilot
Preparation tasks related to the software components | from Software Component Matrix (for E-.ARK tools) | from Scenarios sheet | from Processes sheets | Yes /No / (issue) | Yes / (planned date of availability) | Installed / (issues) | No needed / Configured / (issues) | Yes / (issues) | Ready / (issues)
SIARD2.0 | dbptk-app v2.0.0-beta5 | Scenario 1 | Pre-igest | Yes | Yes | v. 5 | Planned by 28.03.2016 | Yes | Ready
SIARD2.0 | dbptk-app v2.0.0-beta5 | Scenario 2 | Pre-igest | Yes | Yes | v. 5 | Planned by 28.03.2016 | Yes | Ready
SIARD2.0 | dbptk-app v2.0.0-beta5 | Scenario 3 | Pre-igest | Yes | Yes | v. 5 | Planned by 01.09.2016 | Yes | Ready
SIARD2.0 | dbptk-app v2.0.0-beta5 | Scenario 4 | Pre-igest | Yes | Yes | v. 5 | Planned by 01.10.2016 | Yes | Ready
Preparation status
Pilot dataset | Dataset # | Scenario | Data selected | Legal issues | Data available | Dataset ready for Pilot
Preparation tasks related to pilot data | from Pilot Data sheet | from Scenarios sheet | Yes / (issues) | None / (issue) | Yes / (planned date) / (issue) | Ready / (issue)
EBA | Data set 1 | Scenario 1, 2 | Yes | None | Yes | Yes
Client of EBA | Data set 2 | Scenario 3, 4 | Yes | Contract | Yes | Yes
Prepration status
Infrastructure | Scenario | Process | Element selected | Issues | Element ready for Pilot
Preparation tasks related to pilot infrastructure | from Scenarios sheet | from Processes sheets | Yes / (issues) | None / (issue) | Ready / (issue)
Installation of Database Preservation Toolkit | Scenario 1, 2, 3, 4 | Pre-ingest | Yes | None | by 29.03.2016
Preparation of test environment (data re-migration) | Scenario 1, 2, 3, 4 | Pre-ingest | Yes | None | by 08.04.2016
Note on A4: Please, list all relevant E-ARK and local software components. Example: - Data Preservation Toolkit - XIP Creator (local)
Note on C4: Please, select the scenario from the Pilot Scenarios sheet in which the tool is used
Note on D4: Please, select the process from the processes sheets in which the tool is used. Example: - Pre-Ingest - Access
Note on E4: Please, indicate whether the tool has benn selected (yes) or not yet (no), and any issues related tool selection (like: "Testing tool candidates")
Note on F4: Examples: - Yes - 01/04/2016 - No date available
Note on G4: Examples: - Installed - Planned at 01/04/2016 - Installation issues - No instal kit available
Note on H4: Examples: - No configuration needed - Configured - Configuration issues
Note on I4: Examples: - Yes - Training required - Further knowledge transfer needed - User Manual not available
Note on A16: Please list every data set from the Pilot Data sheet
Note on C16: Please, select the scenario from the Pilot Scenarios sheet in which the dataset is used
Note on D16: Please indicate wheather the data set has been selected yet
Note on E16: Example: - None - Under contracting with provider - Under negotiaitions with provider
Note on F16: Example: - Yes - 01/04/2016 - dataset not available by provider - access issues
Note on A23: Please list all infrastructure components that are relevant (and not obvious) for the pilot Like - special hardware elements - special database elements - special data viewers (not provided by E-ARK)
Note on B23: Please, select the scenario from the Pilot Scenarios sheet in which this infrastructure component is used
Note on C23: Please, select the process from the processes sheets in which this infrastructure component is used. Example: - Pre-Ingest - Access
Note on D23: Please indicate wheather the element has been selected yet

## Pre-Ingest
OAIS Process | Pre-Ingest
Main Process Stepps | Content definition Technical feasibility Legal issues etc. | Create/Review transfer agreement | Select data | Data Extraction | Manual compilation of non ERMS content | Metadata mapping | Create SIP | Post-packaging quality control | Submit SIP
Scenario 1 | Migration and Ingest of MS-SQL database in SIARD 2.0 format
Used E-ARK tool |  |  |  | Database Preservation Toolkit |  |  | RODA-in
Used local tools | Gathering agreements to use data for testing purpose. | [7 empty] | Local tools
Perfomer (actor) | Manager |  | Specialists | Specialist |  |  | Specialist |  | Specialist
Prelemineries and Start condition |  |  | Populate test database with production data
Input | Contracts |  | Set of production database | Database |  |  | SIARD 2.0 |  | E-ARK SIP Local SIP
Output | Permission |  | Database for testing | SIARD 2.0 |  |  | E-ARK SIP Local SIP

## Ingest
OAIS Process | Ingest
Main Process Stepps | Receive SIP | Security check | Integrity check | Sintax check | Format check | Review and Approve SIP | Modify SIP | Generate and Store AIP
Scenario 1
Used E-ARK tool
Used local tools
Perfomer (actor)
Prelemineries and Start condition
Input
Output

## Backup Lists
OAIS Processes
Pre-Ingest
Ingest
Preservation
Data Management
Access
IP Formats
E-ARK SIP format
non-E-ARK SIP format
E-ARK AIP format
non-E-ARK AIP format
E-ARK DIP format
non-E-ARK DIP format
Pre-Ingest Use-cases
Extract and Ingest relational database based on SIARD 2.0
Extract and Ingest ERMS records based on MoReq2010
Extract and Ingest computer files from simple file-system - GML
Extract and Ingest computer files from simple file-system - Other (please specify)
Other (please specify in the Note field)
Native metadata format of producer system
MoReq 2
MoReq 2010
ApeEAD
EAD 1
EAD 2
EAD 3
Other (Please specify in the Note field)
Pre-Ingest Process Steps
Content definition, technical feasibility, legal issues, etc.
Create/review transfer agreement
Select data
Manual compilation of non ERMS content
Data extraction
Metadata mapping
Create SIP
Post-packaging control
Submit SIP
Receive SIP
Security check
Formal validation
Content review and approval
Modify SIP
Generate and store AIP
Search & Order Management
DIP Preparation
DIP Delivery
DIP Management
Other (please specifiy)
Pre-Ingest / Ingest Tools
Alfresco Export Module for MoReq2010-based extraction
ESSArch Tools for SIP preparation and creation
Database Preservation Toolkit for creating SIARD2.0 from relational
SIP-AIP Module
Other non-E-ARK tool (please specify)
Access Tools
Search Module
Order Module
DIP Management Module
AIP-DIP Module
Presentation Module
Other non-E-ARK tool (please specify)
Access Use-cases
Access databases via Sofia (sql)
Access databases via SOLR (no-sql)
Access single ERMS records via alfresco cms
Access geodata via qgis
Access data with OLAP via oracle
Other (please specify content type and presentation tool)